## Slide 1
PROJECT MANAGEMENT
CHANGEMAKER PROGRAM
Bronwyn Oatley @BronwynOatley

## Slide 2
OBJECTIVES
Introduce project management methods, including Agile, Lean, and the Iron Triangle
Surface project planning management essentials and common pitfalls
Develop project timelines
Identify relevant project management tools
Bronwyn Oatley @BronwynOatley

## Slide 3
INTRODUCTIONS
Bronwyn Oatley @BronwynOatley
Notes: Name
What you get up to during the day
A few words on your project idea
First word that comes to your mind when you think about project management

## Slide 4
INTRODUCTIONS
Your name
What you get up to during the day
A few words on your project idea
The first word that comes to your mind when you think about project management
Bronwyn Oatley @BronwynOatley

## Slide 5
PROJECT MANAGEMENT
Bronwyn Oatley @BronwynOatley

## Slide 6
@BronwynOatley
WHY DO WE PLAN?

## Slide 7
Why Plan?
Establish a common vision for a project
  Identify common, and dissimilar objectives amongst teammates
  Identify our assumptions, biases amongst teammates
  Establish what success would look like
  Identify timelines, deliverables etc.
Set team ground rules
  Time/ location of meetings
  Roles
  Amount of work
  Hierarchy
Determine scope, budget and quality of project
Others?
Bronwyn Oatley @BronwynOatley

## Slide 8
@BronwynOatley
WHAT SHOULD BE IN A PLAN?

## Slide 9
@BronwynOatley
WHAT SHOULD BE IN A PLAN?

## Slide 10
What should be in a plan?
Exactly what’s needed to achieve your outcomes, which might include consideration of some of the following things:
  Project objectives and key deliverables
  Key project activities
  Timeline
  Budget
  Scope
  Team, roles, values, approach to work
It might also include sub-plans focused on:
  Fundraising
  Communications
  Project ideation, design, implementation, evaluation
  Community engagement/ participation
Others?
Bronwyn Oatley @BronwynOatley

## Slide 11
@BronwynOatley
YOUR APPROACH

## Slide 12
Pair Discussion: What is your approach to project management?
Describe a project you’ve helped to plan or manage.
What parts of it you actively ‘manage’? What did you do out of necessity?
What worked best? What worked least well?
What are some of your personal strengths when it comes to project management? What are some areas for improvement?
Bronwyn Oatley @BronwynOatley

## Slide 13
Group Discussion: Project Management Musts
What are some of the most useful project management tools/ approaches we use?
What are some of the approaches/ things that most often hold us back?
Bronwyn Oatley @BronwynOatley

## Slide 14
@BronwynOatley
IRON TRIANGLE
SCOPE
BUDGET
SCHEDULE
QUALITY

## Slide 16
Iron Triangle Take-Aways
It can be helpful to determine / ask about scope, budget and schedule.
It can be useful to consider that it can be tough to have it all (inexpensive, quick, and high-quality)
It can be useful as a team to prioritize among the three
Bronwyn Oatley @BronwynOatley
MOST USEFUL IF: Your project deliverables, timeline, and budget are clear

## Slide 17
AGILE

## Slide 18
AGILE Take-Aways
Consider working in ‘sprints’, building your list of upcoming tasks based on what most needs to be done before evaluating your work
Consider team roles and and assigning a ‘Product Owner’ and ‘Scrum Master’ role
Might it work for your team to try and keep meetings brief, only reviewing what is most pertinent to the day ahead?
Bronwyn Oatley @BronwynOatley
MOST USEFUL IF: Your building a project that faces tight timelines, and is quite complex (and could be taken in lots of different directions)

## Slide 19
@BronwynOatley
LEAN STARTUP

## Slide 21
Lean Startup Take-Aways
Entrepreneurship is about testing hypotheses
What separates great entrepreneurs from bad ones is that great ones know when to pivot (and how to pivot)
Good entrepreneurship is about creating something that people actually want/ that the user actually needs
What should be in your MVP? Only what you need to advance your learning / test your hypothesis about what your user needs.
Start with your riskiest assumption
Bronwyn Oatley @BronwynOatley
MOST USEFUL IF: How you ‘solve’ your problem is unknown AND you’re working with a team that’s comfortable with moving and adapting quickly

## Slide 22
@BronwynOatley
DESIGN THINKING

## Slide 23
PAIR DISCUSSION
Bronwyn Oatley @BronwynOatley
WHICH APPROACH MIGHT BE MOST USEFUL FOR YOU?

## Slide 24
BREAK
Bronwyn Oatley @BronwynOatley
15 MINUTES

## Slide 25
BREAK
Bronwyn Oatley @BronwynOatley
15 MINUTES

## Slide 26
ACTIVITY PROJECT TIMELINES
Bronwyn Oatley @BronwynOatley

## Slide 27
DESIGN SPRINTS
Bronwyn Oatley @BronwynOatley
Discovery
Sketch competing solutions
Choosing a Hypothesis to test
Create a prototype
Test it with humans

## Slide 28
Prompts:
Plot our your project’s timeline, building on the calendar provided or using a preferred calendar tool.
Consider including:
  Key project deliverables (f known, if possible to estimate)
  Additional relevant dates, including: team meetings, stakeholder meetings, Changemaker Workshops, related dates that might influence your work.
  Consider including ‘project phases’, ex. “Discovery, Design, Delivery, Evaluation”
  Upcoming tasks to be completed (consider using the Agile approach of developing spring or product backlogs)
If relevant, generate a list of questions you need answers in order to complete your project timeline.
Bronwyn Oatley @BronwynOatley

## Slide 29
PAIR & SHARE:
What’s best about your partner’s timeline?
What could be improved?
Bronwyn Oatley @BronwynOatley

## Slide 30
GROUP DISCUSSION
What needs to be included in our plans?
Bronwyn Oatley @BronwynOatley

## Slide 31
USEFUL TOOLS
Project Management Tools: Smartsheet, Asana, Basecamp
Calendar Tools: Google Calendar, Outlook
Meeting Organization Tools: Doodle
Virtual Meeting Tools: Skype, Google Hangout
Digital Storage Tools: Google Drive, Dropbox
Bronwyn Oatley @BronwynOatley

## Slide 32
CONCLUSION
Bronwyn Oatley @BronwynOatley